## Sheet1
Task Name | Duration
Project Charter | 2 days
Project Estimates Approval | 1 day
Project kickoff
Project Planning
Project Management Plan | 1 day
Resource Plan | 1day
Launch Execution
DEVELOPMENT
Software Framework
Drupal Installation on Dev | 0.5 days
Roles, Permissions | 2 days
Content Workflow Setup | 2 days
Digital Branding | 0.5 days
Server Architecture
Test/Stage setup | 1 day
DB automate scripts | 1 day
3rd party module integration | 2 days
API integration - Newsletter | 1 day
Close of Development
DATA MIGRATION
Product info (all data) | 4 days
Corporste Pages | 1 day
TESTING
User Acceptance Testing (UAT) | 3 days
DEPLOYMENT
Site Admin Training and Handover | 2 days
Project Closure